## Sheet1
North Kent Woods and Downs Management Framework Actions last updated Sep 2025 | Lead | By when | Priority score | Progress | Core purpose | Secondary core purpose | Link to strategy same links with hyperlinks found in Management Framework tables
N1: Collaborative grazing • Creating infrastructure across the NNR to support small graziers and make grazing easier • Explore and establish NNR/conservation meat marketing and branding opportunities • Purchase of stock either for partners or local graziers | National Trust, Birling Estate, Kent County Council CP |  | 5 |  | Nature |  | Grazing Strategy – particularly recommendations on p15 Landscape Implementation Plan – particularly fencing design information on p33
N2: Chalk grassland restoration • Use of green hay to enhance chalk grassland restoration sites • Draw up and implement scrub removal/management programme • Collaborate with Big Chalk initiative | National Trust, Kent County Council CP, Kent Downs NL |  | 5 |  | Nature |  | Grazing Strategy – particularly recommendations on p15 Environmental and ecological strategy – particularly recommendations on p47 Botanical and habitat assessment Herpetological assessment – particularly reptile recommendations on p44 Orthoptera, mollusc, bug and hymenoptera assessment Fungal assessment – particularly recommendations for waxcap communities on p12
N3: Cluster collaboration • Maintain and develop strong links with farm clusters and other collaborative initiatives • Develop, fund and deliver joint projects with other clusters/initiatives | Birling Estate |  | 5 |  | Nature | People | No specific links to strategies and implementation plans but Chalk to Coast is an obvious example
N4: Woodland connectivity • Map areas to be targeted for woodland connectivity improvements • Plan and deliver specific actions e.g. hedgerow planting, softening woodland edges, connecting isolated woodland • Plan and implement ride management for wildlife and fire management • Monitor for species likely to benefit from actions such as dormice | National Trust, Plantlife, People’s Trust for Endangered Species |  | 5 |  | Nature | Science | Environmental and ecological strategy – particularly recommendations on p47 Botanical and habitat assessment plus habitat mapping to identify gaps in linkage – Bat assessment – particularly table 9 on p17 Mammal assessment – particularly opportunities section on p22 Saproxlic assessment – particularly recommendations on p31 Landscape Implementation Plan – particularly distinctive landscape patterns on p16
N5: Veteran tree plan implementation • Implement veteran tree management plan developed for the NNR including haloing, retrenchment pruning and soil improvement • Veteranisation of selected trees • Plan for and plant areas with no future veterans • Implement plan to retain hornbeam within the landscape | National Trust, Woodland Trust |  | 5 |  | Nature |  | Ancient and veteran tree survey and strategy – particularly recommendations on p25 as well as individual tree management plans (not available online but in files sent by Treework Environmental Practice)
N6: Sustainable woodland management • Find host site and create shared tree nursery • Target and map areas for regeneration (restoration of coppice regime, increase tree species diversity, access enhancements for timber extraction). • Implement plan | Silverhand Estate, Plantlife |  | 4 |  | Nature |  | Environmental and Ecological Strategy Strategy – particularly recommendations on p47
N7: Wet woodlands, ponds and rewetting • Map all wet areas and ponds • Identify and implement pond creation and rewetting areas • Identify areas to improve connectivity of wetland areas | Kent County Council CP, Kent Downs NL, National Highways |  | 4 |  | Nature |  | Botanical and habitat assessment plus habitat mapping to identify wet woodland Herpetological assessment – particularly amphibian recommendations on p34 Climate Change Vulnerability Assessment found in annex 2 of the Environmental and ecological strategy – as well as pond creation mapping created by White Horse Ecology (unpublished but GIS mapping available from Kent Downs or White Horse Ecology)
N8: Keystone species reintroduction and other reintroductions • Explore feasibility of reintroduction programmes. Specifically for beaver and pine marten | Birling Estate |  | 3 |  | Nature | Science | Not explored in detail in any of the strategies but info available online and refer to KWT/Wildwood Trust Pine Marten reintroduction project
N9: Extend arable plant areas • Identify areas to encourage arable plants • Establish trial plots to explore management techniques • Expand areas where arable plant agri-environment scheme options are in place | Plantlife |  | 3 |  | Nature | Science | Botanical and habitat assessment plus habitat mapping to identify areas where arable weeds can be promoted
N10: Mammal management • Continue and refine joined up deer and grey squirrel management • Investigate and trial non-lethal deer management methods • Monitor and react in areas of NNR where no management takes place • Engage with the public | National Trust, Silverhand Estate |  | 3 |  | Nature | Science | Deer strategy and management plan but also Landscape Implementation Plan – particularly deer fencing design on p32
N11: Healthy hedgerows • Agree and deliver co-ordinated programme of planting and layering (link to woodland connectivity action) • Run training events for hedgerow skills for staff and volunteers • Organise volunteering input |  |  | 2 |  | Nature | People | Environmental and ecological strategy – particularly recommendations on p47 Botanical and habitat assessment plus habitat mapping to identify gaps in linkage – Bat assessment – particularly table 9 on p17 Mammal assessment – particularly opportunities section on p22 Saproxylic assessment – particularly recommendations on p31 Landscape Implementation Plan – particularly distinctive landscape patterns on p16
N12: Green bridges • Proactively work with Lower Thames Crossing to maximise biodiversity/access opportunities resulting from the bridges | Kent County Council CP, Gravesham Borough Council, Medway Council |  | 2 |  | Nature | Science | No specific links in strategies but refer to individual taxon assessments where necessary over design
N13: Traditional orchard restoration • Map all areas of traditional orchard in the wider NNR area • Explore the need for restoration and fund restoration • Carry out surveys of invertebrates and fungi • Engage volunteers |  |  | 1 |  | Nature | People | Environmental and ecological strategy – particularly recommendations on p47 Botanical and habitat assessment plus habitat mapping to identify orchards
N14: Dormice studies • Study of biodiversity enhancement corridor for dormice (either woodland or hedgerow) • Monitor rate of population expansion | People’s Trust for Endangered Species, Natural England |  | 0 |  | Nature | Science | Mammal assessment – particularly opportunities section on p22 but review all taxon reports for other ways that hedgerows can be enhanced for priority species
N15: Invertebrate translocations • Review actions and measures from invertebrate studies • Identify and map donor sites for translocations • Monitor hotspots and relocation sites for key species • Exploit engagement opportunities |  |  | 0 |  | Nature | Science | Taxon studies, in particular saproxylic invertebrates, orthoptera, molluscs, bugs and hymenoptera, lepidoptera, coleoptera, aranae, diptera and odonata
N16: Going underground (cables) • Identify and pursue overhead cable undergrounding opportunities | Kent Downs NL |  | 0 |  | Nature |  | Landscape Implementation Plan – particularly visual landscape enhancements on p17
N17: Holistic land management of the ‘Leisure Plots’ • Secure commitment from key stakeholders • Pursue options for securing the holistic management of the land | Kent Downs NL, Gravesham Borough Council, Medway Council, National Trust, West Kent Downs Countryside Trust |  | 5 |  | Nature |  | No specific links in strategies but documents supporting the proposal and minutes of meetings available from Kent Downs NL.
S1: Future tree species • Conduct research including trials to identify appropriate new species for the area and build resilience to climate change • Produce report and share across and beyond the NNR | Woodland Trust |  | 5 |  | Science | Nature
S2: Seeing the wood pasture from the trees • Explore the historic landscape through trees and produce report • Work with Forestry Commission to combat veteran tree losses | National Trust, Birling Estate |  | 4 |  | Science | People | Heritage theme 1: landscape and environment Landscape Implementation Plan – particularly heritage landscape on p30 and Climate Change Vulnerability Assessment found in annex 2 of the Environmental and ecological strategy plus veteran and ancient tree survey
S3: Climate change research and monitoring • Ongoing monitoring of impact using citizen science and experts • Monitor impact of management interventions • Monitor carbon storage and sequestration of land management techniques in NNR • Monitor colonisation of species and record losses of vulnerable species (e.g. adder) • Review and update Climate Change Vulnerability Assessment | All |  | 4 |  | Science | Nature | Climate Change Vulnerability Assessment found in annex 2 of the Environmental and ecological strategy though this action requires in depth monitoring of priority species and others that are particularly sensitive to climate change. These are identified in the taxon reports
S4: Species research and monitoring • Action priority measures from species reports • Plan recording and monitoring programme using volunteers and experts including Bioblitzes • Share results with the public and other research institutions • Set up data sharing agreement with KMBRC | All |  | 4 |  | Science | People | All taxon reports and Community Engagement Plan on p 77 of Visitor Access and Engagement strategy and implementation plan
S5: Wood marketing and best practice • Review current marketing practices • Identify new avenues for marketing wood products and adding value • Share learning and best practice | Birling Estate, Savills |  | 3 |  | Science | People | No specific links in strategies but relevant to implementation of recommendations within Environmental and ecological strategy and all taxon reports.
S6: Academic institution partnerships • Develop and foster NNR wide, long-term relationships with academic institutions building on existing links • Create a list of research briefs to share with institutions around management regimes and conservation of key species | Plantlife |  | 3 |  | Science |  | No specific links to strategies but an overarching approach to recommendations in taxon reports in particular
S7: Hydrology and soil research • Baseline soils and hydrological processes across NNR • Use to help mitigate climate change impact |  |  | 3 |  | Science | Nature | Climate Change Vulnerability Assessment found in annex 2 of the Environmental and ecological strategy
S8: Archaeological sensitivity mapping • Develop GIS based archaeological sensitivity mapping for NNR • Use mapping to guide potentially harmful management activities • Use mapping to support a research framework for the NNR | KCC Heritage, Kent Downs NL, National Highways |  | 3 |  | Science |  | Information in the Heritage strategy and its implementation plan
S9: Air pollution research and monitoring • Monitor baseline • Monitor changes during construction of Lower Thames Crossing • Identify hotspots and possible methods of minimising impact | Kent Downs NL, National Highways |  | 2 |  | Science |  | No direct links to strategies though relevant to the Climate Change Vulnerability Assessment and the pollution sections of the Environmental and ecological strategy
S10: Historic Environment Record audit • Full audit of HER across the NNR • Clear the archaeology backlog. Project research from the area already undertaken to be added to the HER • Create GIS based sensitivity mapping to guide archaeological mitigation and research • Link with KCC Heritage Public Access and Community Engagement (PACE) strategy to engage with public | KCC Heritage |  | 2 |  | Science |  | Information in the Heritage strategy and its implementation plan
S11: Industrial heritage research • Research programme to detail industrial heritage – build on work by Chris Down • Archaeological investigations • Use to guide site specific management guidance | Tarmac, KCC Heritage |  | 2 |  | Science |  | Recommendations in the Heritage strategy and in particular the industry appendix
S12: Agricultural heritage audit • Research history of farming and wood pasture within the NNR supported by research being carried out by Geoff Baker • Document why landscape looks as it does today • Create interpretation and engagement resources | KCC Heritage, Plantlife, National Trust |  | 2 |  | Science |  | Recommendations in the Heritage strategy and in in the agriculture appendix when completed by Geoff Baker (ex Gravesham Borough Council)
S13: Marvellous Mesolithic (plus Palaeolithic and Neolithic) • Additional research into the potentially significant findings at Ranscombe Farm • Expand other areas of Holocene research • Identify opportunities for engagement | Plantlife, KCC Heritage |  | 1 |  | Science | People | Information in the Heritage strategy and its implementation plan
S14: A towering success • Measure the impact of ‘wildlife towers’ at Silverhand Estate • Share learning and experience including various methods of replicating what has worked • Create engagement opportunities around the towers | Silverhand Estate |  | 1 |  | Science | Nature | No specific links to the strategies
S15: Indicators of change • Develop set of metrics to measure change using CS option indicators, SSSI common standards monitoring • Link to LNRS habitat targets | Natural England, Kent County Council Natural Environment and Coasts |  | 1 |  | Science | Nature | No specific links to the strategies
S16: Natural capital and green finance (to include NE agri-environment schemes) • Research potential of options available and report to NNR partners and neighbours • To include the possibility of combining, or at least harmonising the start and end dates, of all NNR agri-environment schemes • Develop strategy to maximise benefit of green finance | Kent Downs NL, Natural England | 2030 | 1 |  | Science | People | No specific links to the strategies
P1: Grazing Animals Project (GAP) • Raising awareness of grazing animal projects and education around human/dog/grazing animal conflict • Identify priorities for footpath and signage maintenance • Could link with N1: collaborative grazing |  |  | 5 |  | People |  | Grazing strategy including recommendations section from p15 onwards
P2: Network of NNR routes and trails • Manage access appropriately maintaining tranquil areas and signposting official camping etc. • Plan and map improvements • Monitor visitor numbers (including using new technology) • Monitor impact of visitors on biodiversity • Coherent and consistent interpretation and signage • Shared usage opportunities and circular routes linking to public transport • Access and marketing campaign | Kent County Council CP and PROW, Medway Council | Ongoing | 4 |  | People | Nature | Plans C to H on pages 71 to 76 of the visitor access and engagement strategy as well as the Visitor Access Implementation plan on p85 onwards
P3: Accessible trails for all • Appropriate access for all paths where feasible • Accessibility audits of major routes and upgrades • Ensure links with and carried out at the same time as P2 | Kent County Council CP |  | 4 |  | People |  | Plans C to H on pages 71 to 76 of the visitor access and engagement strategy as well as the Visitor Access Implementation plan on p85 onwards. Also consult the Outdoor Accessibility Guidance from Paths for All and The Sensory Trust as well as work undertaken b the North Downs Way
P4: Countryside skills hub • Develop centre of excellence to develop skills in: o Ecological skills o Countryside skills o Heritage skills o Apprenticeships • Link to local colleges where appropriate and to secure funding |  |  | 4 |  | People | Nature | Information in the visitor access and engagement strategy and in particular the community engagement implementation plan on p77 onwards
P5: Harnessing citizen science • Plan and deliver suite of monitoring activities and link to P9: Collaborative volunteer programmes • Develop training for volunteers and input from species specialists |  |  | 3 |  | People | Science | Information in the visitor access and engagement strategy and in particular the community engagement implementation plan on p77 onwards. Ideas for how volunteering recording can be harnessed in most of the taxon group reports
P6: Vistas and viewpoints • Public engagement in identifying favourite views in the NNR • Use Landscape Character Assessment implementation plan to guide promotion and interpretation of viewpoints | Kent Downs NL |  | 3 |  | People |  | Landscape Implementation Plan – particularly community consultation section starting on p20
P7: Woodland skills • Organise training to ensure woodland skills survive possibly as part of P4: Countryside skills hub | Kent County Council CP |  | 3 |  | People |  | Information in the visitor access and engagement strategy and in particular the community engagement implementation plan on p77 onwards
P8: Engagement with schools • Create NNR ‘schools pack’ • Identify barriers to schools (e.g. pool of outdoor clothing/transport) • Link to curriculum around countryside usage • Funding for outreach to promote NNR within schools | Kent County Council CP |  | 3 |  | People |  | Information in the visitor access and engagement strategy and in particular the community engagement implementation plan on p77 onwards
P9: Collaborative volunteer programmes • Co-ordinated NNR wide volunteer opportunities (e.g. lookering) • Identify and create mechanism to communicate and recruit volunteers • Set up roving volunteer group • Volunteer co-ordinator role |  |  | 3 |  | People | Nature | Information in the visitor access and engagement strategy and in particular the community engagement implementation plan on p77 onwards
P10: Better byways • Map weak points in the Byway network where antisocial behaviour likely to occur • Secure weak points • Raise awareness of acceptable byway usage | Silverhand Estate |  | 2 |  | People |  | Information in the visitor access and engagement strategy and in particular the visitor access implementation plan on p85 onwards
P11: Apprenticeships • Scope potential for apprenticeships across the NNR including shared training of apprentices • Identify routes for funding apprenticeships |  |  | 2 |  | People | Nature | Information in the visitor access and engagement strategy and in particular the community engagement implementation plan on p77 onwards
P12: Urban access gateways, hubs and transport • Identify sites for improvements/enhancements as gateways to the NNR with particular consideration for car parking • Map opportunities for enhanced connectivity to transport hubs and urban areas • Consider new greenspace, open areas which are part of potential mitigation for other development (SANGS) and how they could best fit with the NNR • Links to Cyclopark and new Gravesham Borough Council site near Ifield • New visitor hub | Kent County Council CP, Medway Council, Gravesham Borough Council, Plantlife |  | 2 |  | People | Nature | Information in the visitor access and engagement strategy and in particular the visitor access implementation plan on p85 onwards
P13: Integrated interpretation • Tailored approach for different sites that provides cohesion for NNR message while respecting the current brands • Community participation in interpretation | Kent County Council CP |  | 2 |  | People |  | Information in the visitor access and engagement strategy and in particular the visitor access implementation plan on p85 onwards
P14: Breaking down barriers • Identify barriers to access for the NNR (experts/consultations) though some already identified in Visitor Access and Community Consultation reports in annexes • Implement findings |  |  | 2 |  | People |  | Information in the visitor access and engagement strategy and in particular the community engagement implementation plan on p77 onwards
P15: The youth voice • Set up NNR Youth Forum • Implement actions recommended by forum and provide opportunities to get involved • Ensure forum has a voice in governance of the NNR |  |  | 2 |  | People |  | Information in the visitor access and engagement strategy and in particular the community engagement implementation plan on p77 onwards
P16: Learning and engagement lead post • Expand on Plantlife plan to develop post at Ranscombe Farm and make the initiative NNR wide | Plantlife |  | 1 |  | People |  | Information in the visitor access and engagement strategy and in particular the community engagement implementation plan on p77 onwards
P17: Harnessing multiple media • Use wide range of media from Countryfile to TikTok and Instagram to promote the NNR • Recruit someone to lead this work and fund the post |  |  | 1 |  | People |  | No specific links in strategies to this action
P18: Health and wellbeing projects • Commission report to look at potential NNR initiatives to align with the health agenda • Be more active in engaging with green prescribing | Natural England, NHS, local authorities |  | 1 |  | People |  | Information in the visitor access and engagement strategy and in particular the community engagement implementation plan on p77 onwards
P19: Forest school development • Explore opportunities to expand Forest School initiatives • Designate drop off points to broaden access of Forest Schools to more than just nearby villages | Plantlife, Birling Estate |  | 0 |  | People |  | Information in the visitor access and engagement strategy and in particular the community engagement implementation plan on p77 onwards
P20: Engagement events calendar • Develop year-round calendar of events across the landscape • Include wider partnership events • Canvas target audiences to identify need for events | Kent Downs NL |  | 0 |  | People |  | Information in the visitor access and engagement strategy and in particular the community engagement implementation plan on p77 onwards
P21: NNR in 3D • Extensive LIDAR Mapping of NNR • Develop fly through of NNR • Allow fly throughs at different points in time | KCC Heritage |  | 0 |  | People | Science | Alluded to in the heritage strategy and directly mentioned in the implementation plan